# Hampton Family Dental — Master Project Handoff

Purpose of this doc: Complete context transfer so the whole project can move into Cowork without losing history. Everything below — the situation, decisions, files, blockers, and next steps — is current as of June 18, 2026.

Prepared by: Vicky Lalwani, Digital Marketing Director — Softqube Technologies (softqubes.com)

## 1. PROJECT IN ONE PARAGRAPH

The dental practice formerly known as Brenner Dental Group (Southampton, PA) has been acquired and is rebranding to Hampton Family Dental. We (Softqube) are handling the full transition: a brand migration, an SEO migration (protecting the rankings Brenner already earned), a rebuild of the new website from a one-pager into a proper multi-page site, local SEO, Google Ads, and ongoing growth. The new site is being built by our developer Nirav in Next.js. This is not just a redesign — it's protect-what-exists + build-what's-new.

## 2. KEY FACTS (memorize these)

| Item | Detail |
| --- | --- |
| Old brand | Brenner Dental Group |
| New brand | Hampton Family Dental |
| Old website | https://www.brennerdentalgroup.com/ (Duda platform — blocks crawlers) |
| New website (in dev) | https://hampton-family-dental.vercel.app/ (Next.js) |
| Address | 283 Second Street Pike, Suite 140, Southampton, PA 18966 |
| Phone | (215) 357-2224 → tel:+12153572224 |
| Two dentists | Dr. Jeffrey Brenner (founder) + Dr. Keyur Dudhat (new partner) |
| Reference site #1 | https://www.amazingsmilesbydesign.com/ (Dr. Dudhat's current practice — clone this structure) |
| Reference site #2 | https://www.elegantedgedentistry.com/ |
| Target area | Tier 1: Southampton + 18966. Tier 2: Richboro, Warminster, Newtown. Tier 3: Holland, Feasterville, Huntingdon Valley, Churchville |
| Final domain | NOT YET CONFIRMED (blocks launch + redirects) |

People:

- Hari Krishna Patel — CEO, Softqube

- Nitinkumar Suvagia — senior decision-maker

- Nirav Bhadani — developer (builds the site; receives our briefs)

- Vicky Lalwani — digital marketing lead (you)

- Rakeshbhai — new practice owner (client side)

## 3. THE SINGLE MOST IMPORTANT FINDING

The new Hampton site is STILL A ONE-PAGE SITE with a placeholder dentist ("Dr. James Hampton") and wrong location text ("Hampton, NY"). Almost nothing from our developer briefs has been implemented yet as of the last check. This is the core problem the whole project is working to fix.

Why it matters for SEO: The old Brenner site ranks for real money keywords. If we don't build matching real pages + 301-redirect them, those rankings vanish at launch. Current rankings to protect:

| Keyword | Old site position | New page needed |
| --- | --- | --- |
| dental implants southampton pa | #2 | /restorative-dentistry/dental-implants |
| emergency dentist southampton | #3 | /general-dentistry/emergency-dentistry |
| preventative dentistry southampton | #3 | /general-dentistry (hub) |
| southampton invisalign | #4–7 | /cosmetic-dentistry/invisalign |
| dentist southampton pa | #7 | / (homepage) |
| dentures southampton | #7 | /restorative-dentistry/dentures |
| 18966 dentist | #4 | / (homepage) |

Old site authority snapshot (Semrush): Authority Score 15, ~281 referring domains, ~1,508 backlinks, ~73 organic keywords, ~75 organic visits/mo. Small but real — worth protecting via redirects.

## 4. LOCKED DECISIONS (do not re-litigate)

- Build multi-page, not one-page. Real URL per service.

- Two dentists only: Dr. Jeffrey Brenner + Dr. Keyur Dudhat. Remove "Dr. James Hampton" everywhere.

- EXCLUDE these services (practice doesn't offer): Sedation Dentistry and Pediatric Dentistry. No pages, no keywords, no schema, and remove "pediatric dentistry" from homepage meta keywords.

- Services IN scope: General (oral hygiene, checkups/x-rays, emergency, extraction, oral cancer screening, Perio Protect), Restorative (implants, crowns, bridges, fillings, root canal, dentures), Cosmetic (veneers, Invisalign, ClearCorrect, whitening, bonding, smile makeover).

- Navigation: NO "Home" tab (logo links home). Menu = Patient Information ▾ · General Dentistry ▾ · Restorative Dentistry ▾ · Cosmetic Dentistry ▾ · About Us ▾ · Specials · Contact Us · [Schedule Now] · [Call]. Dropdowns hover on desktop, accordion on mobile; parent labels link to hub pages.

- Brand bridge: Run "formerly Brenner Dental Group" on homepage hero + About + footer for continuity.

- Membership plans confirmed: Child $312/yr · Adult $369/yr · Perio $569/yr · 15% off other procedures · 10% off Ortho & Implants. Lives on /specials, marketed hard to no-insurance patients.

- New logo + color palette coming from client — entire site palette changes to match (tokenize CSS colors). Current dark "luxury" theme goes away.

- Content standard: money service pages 1,500+ words, standard service pages 1,200+, hubs 500–800, with full keyword placement + FAQ schema. A page below the bar won't rank.

- Local strategy: Richboro/Warminster/Newtown have MORE search volume than Southampton — build city pages for them in Phase 2.

## 5. FILES DELIVERED (13 — all in this project's outputs)

### Strategy & planning

| File | What it is | Status |
| --- | --- | --- |
| Hampton_Master_Content_Plan.xlsx | ⭐ THE CONTROL CENTER. 45-page sitemap + content workspace + keyword map + content standards + build phases + inputs-needed. Work from this. | Live tool |
| Hampton_Keyword_Strategy.xlsx | 10-tab keyword research: SEO primary/secondary, local, GBP, Ads campaigns + negatives, AEO questions, brand bridge, equity-to-defend | Reference |
| Hampton_Action_Plan.xlsx | 33-item action plan (existing site + new site + migration + growth) + missing inputs + 30-day plan | Reference |
| Hampton_Developer_Brief_v3.md | Full build spec for Nirav (architecture, nav, placeholder fixes, content map, 17 sections) | Reference |

### Client-facing

| File | What it is |
| --- | --- |
| Hampton_Family_Dental_Client_Presentation.pdf / .pptx | 13-slide client deck (migration story, scenarios, roadmap) |
| Hampton_Family_Dental_Strategy.docx | Premium strategy document (exec summary, scenarios, growth engine, one-pager) |
| Hampton_Family_Dental_Execution_Workbook.xlsx | 6-tab execution workbook (current situation, migration checklist, site architecture, redirect map, PPC, roadmap) |

### Page content written (each = paste-ready, page-by-page, with meta + keywords + copy + FAQ + schema + dev checklist)

| File | Page | Word target | Status |
| --- | --- | --- | --- |
| Hampton_Homepage_Content.docx | Homepage / | ~1,100 | Drafting |
| Hampton_Dental_Implants_Content.docx | /restorative-dentistry/dental-implants | 1,500+ | Drafting |
| Hampton_Emergency_Dentistry_Content.docx | /general-dentistry/emergency-dentistry | 1,200+ | Drafting |
| Hampton_Invisalign_Content.docx | /cosmetic-dentistry/invisalign | 1,500+ | Drafting |
| Hampton_Service_Hub_Pages_Content.docx | 3 hubs (General, Restorative, Cosmetic) | 600–700 each | Drafting |

Content progress: 7 of 45 pages drafted (Homepage + 3 ranking-protection pages + 3 hubs).

## 6. CONTENT STATUS — WHERE EACH PAGE STANDS

### ✅ Drafted (7) — ready for your review, then to Nirav

- Homepage

- Dental Implants (protects #2)

- Emergency Dentistry (protects #3)

- Invisalign (protects #4–7)

- General Dentistry hub

- Restorative Dentistry hub

- Cosmetic Dentistry hub

### ⛔ Blocked on inputs (2)

- Dr. Jeffrey Brenner bio page — needs real bio + photo

- Dr. Keyur Dudhat bio page — needs real bio + photo

### ⬜ Not started yet (remaining ~36), in priority order

- Conversion: /specials, /contact, /patient-information/scheduling, /patient-information/new-patients

- Service pages: dental crowns, teeth whitening, dental fillings, dentures, Perio Protect, ClearCorrect, porcelain veneers, tooth extraction, root canal, dental bridges, oral hygiene, checkups & x-rays, oral cancer screening, dental bonding, smile makeover

- About: our-story, our-team, patient-reviews

- Patient info: why-choose-us, insurance-and-payment, financing-options, emergency-scheduling

- Local city pages (Phase 2): Southampton, Richboro, Warminster, Newtown, Holland, Feasterville, Huntingdon Valley

- Legal: privacy-policy, terms, accessibility

## 7. OPEN ITEMS / INPUTS NEEDED FROM CLIENT (the real blockers)

| # | Need | Blocks | Priority |
| --- | --- | --- | --- |
| 1 | Final domain name | Redirects, canonicals, GBP, launch | HIGH |
| 2 | Dr. Jeffrey Brenner — bio, credentials, real photo | His bio page + doctor blocks; removes fake founder | HIGH |
| 3 | Dr. Keyur Dudhat — bio, credentials, real photo | His bio page + 2nd doctor block | HIGH |
| 4 | Which dentist performs implants / Invisalign | Doctor blocks on those pages | MED |
| 5 | Are current testimonials real? (use real Google/FB reviews if not) | Reviews section + homepage | HIGH |
| 6 | Real practice stats (patient count, review count, rating) | Replace inflated placeholder stats | HIGH |
| 7 | Confirmed office hours | Footer, contact, emergency page | HIGH |
| 8 | Confirm full service list (bridges, root canal, bonding, smile makeover, veneers) | Which pages to build | HIGH |
| 9 | Does practice offer Invisalign brand or only ClearCorrect? | Invisalign page accuracy | HIGH |
| 10 | Insurance plans accepted | Insurance page + schema | MED |
| 11 | New logo + color palette | Site-wide design + color tokens | MED |
| 12 | Real before/after photos (with consent) | Cosmetic + implant pages | MED |
| 13 | GBP admin access | Reviews, citations, local pack | MED |
| 14 | After-hours / emergency line (yes/no) | Emergency page same-day messaging | MED |

## 8. WHAT'S LIVE & WRONG ON THE NEW SITE RIGHT NOW (dev fix list)

These are live on hampton-family-dental.vercel.app and need fixing:

- ❌ "Dr. James Hampton" shown as Founder (fake) → replace with Brenner + Dudhat

- ❌ "Est. 2004 · Hampton · NY" → should be Southampton, PA

- ❌ Still one-page (nav = #home, #about, #services anchors) → build real pages

- ❌ All 8 service cards link to #contact → link to real service pages

- ❌ Title tag "Luxury Dental Care" → "Family Dentist in Southampton, PA"

- ❌ Meta keywords contains "pediatric dentistry" → remove

- ❌ Suite 140 missing from address → add

- ❌ "Schedule Now" → #contact → should be /patient-information/scheduling

- ❌ Stock photo dentist labeled as founder → use real Dr. Brenner photo from old site

- ❌ Privacy/Terms/Accessibility links = "#" → build pages

- ⚠️ Verify testimonials + stats are real, not placeholder

Verified DONE on the site: hours, phone, Southampton PA in hero text, pediatric removed from visible cards, "No Insurance No Problem" CTA, the 3 membership plans block with correct pricing, homepage service-card order.

## 9. HOW THE CONTENT SYSTEM WORKS (the workflow to continue in Cowork)

- Open Hampton_Master_Content_Plan.xlsx → "Content Workspace" tab. Every page is a row in priority order.

- Pick the next page. Pull its keyword from the "Keyword Map" tab (or pull fresh Semrush data).

- Write the content to the standard in "Content Standards" tab (meta title ≤60, meta desc ≤160, H1, H2s, body, 5–8 FAQs, schema, internal links).

- Each page is delivered as its own .docx with 5 sections: A. Metadata · B. Keyword Targets · C. Page Structure & Copy (real words in teal boxes) · D. FAQ with schema · E. Schema + Links + Dev Checklist.

- You review → mark Approved → hand the .docx to Nirav to build.

- Update status in the master plan (Not Started → Drafting → In Review → Approved → Live).

Content pages still follow this exact template — so anyone in Cowork can continue the same way.

## 10. IMMEDIATE NEXT ACTIONS (priority order)

- Get the 14 inputs in Section 7 from the client — especially final domain + both doctor bios/photos. These unblock the most work.

- Send Nirav the Section 8 fix list + the 7 drafted content docs so he can start building real pages (homepage fixes + the 3 ranking-protection pages first).

- Continue content down the priority list: next pages are /specials, /contact, then service pages (crowns, whitening, fillings, dentures).

- Write doctor bios as soon as client provides info (2 pages).

- GBP: keep the existing Brenner profile (rename, don't recreate — saves reviews), update per the GBP tab in the keyword workbook.

- At launch: implement all 301 redirects (old Brenner URLs → new Hampton URLs), submit sitemap, switch GBP website link.

## 11. SEO STRATEGY NOTES (so Cowork has the reasoning)

- Local volumes are small by design. Most "service + city" searches show near-zero volume because patients search "near me" + Google serves the local pack. So we rank in the local pack (GBP + city pages) and capture "near me" through GBP and natural mentions — NOT by chasing exact-match local keywords.

- The big AEO opportunity: "how much are dental implants" (49.5K/mo), "invisalign cost" (74K/mo), "how much is invisalign" (40.5K/mo). Cost questions drive huge volume — every service page has a cost section + cost FAQ to win AI Overviews.

- "Near me" volume is massive: dentist near me (673K), emergency/implants/invisalign near me (90.5K each). Captured via GBP optimization, not blog posts.

- Nearby towns > Southampton: Warminster (210), Newtown (210), Richboro (170) each beat Southampton (170). Newtown implants = 110/mo at $9.89 CPC. Build city pages in Phase 2.

- Brand keywords transition, not disappear: Brenner brand terms (#2–3) will fade as Hampton takes over — we keep those patients via the brand bridge + brand-protection PPC, not by ranking "Brenner" forever.

## 12. PPC QUICK REFERENCE (for when ads start)

- Phase 1 — Brand protection: bid on "Brenner Dental," "Hampton Family Dental," former-brand terms (cheap, defends from competitors during switch).

- Phase 2 — High-intent: emergency dentist, dental implants, Invisalign, cosmetic, family dentist, new patients — Southampton + nearby.

- Phase 3 — Local expansion: Richboro, Warminster, Newtown campaigns.

- Phase 4 — Remarketing: site visitors, form abandoners.

- Every campaign: dedicated landing page + call/form tracking + tight geo + negative keywords (full negative list in the Keyword Strategy workbook — includes "ny," "hampton inn," "hampton university," "james hampton" to block confusion).

## 13. FULL KEYWORD RESEARCH (self-contained — live Semrush US data)

This is the complete keyword set folded in so this doc is self-sufficient. Source: Semrush US, pulled across the project. Reading note on volume: local "service + city" terms often show near-zero monthly volume because patients search "near me" and Google serves the local pack. We rank in the local pack (GBP + city pages) and capture "near me" through GBP + natural mentions. The big measurable volume sits in national "near me" and cost questions — which is where the AEO/FAQ strategy wins.

### 13A. SEO — Primary Keyword per Page (the money map)

| Page (URL) | Primary Keyword | US Vol | KD | Intent |
| --- | --- | --- | --- | --- |
| / | dentist southampton pa | 170 | Easy | Local |
| /restorative-dentistry/dental-implants | dental implants southampton pa | 50 | Medium | Commercial |
| /general-dentistry/emergency-dentistry | emergency dentist southampton pa | low | Easy | Local |
| /cosmetic-dentistry/invisalign | invisalign southampton pa | 50 | Easy | Commercial |
| /cosmetic-dentistry (hub) | cosmetic dentist southampton pa | low | Easy | Commercial |
| /general-dentistry (hub) | general dentistry southampton pa | low | Easy | Local |
| /restorative-dentistry (hub) | restorative dentistry southampton pa | low | Easy | Commercial |
| /cosmetic-dentistry/teeth-whitening | teeth whitening southampton pa | low | Easy | Commercial |
| /restorative-dentistry/root-canal | root canal southampton pa | low | Easy | Local |
| /general-dentistry/tooth-extraction | tooth extraction southampton pa | low | Easy | Local |
| /restorative-dentistry/dentures | dentures southampton pa | low | Easy | Commercial |
| /cosmetic-dentistry/porcelain-veneers | veneers southampton pa | low | Medium | Commercial |
| /restorative-dentistry/dental-crowns | dental crowns southampton pa | low | Easy | Commercial |
| /restorative-dentistry/dental-fillings | dental fillings southampton pa | low | Easy | Local |
| /cosmetic-dentistry/clear-correct | clear aligners southampton pa | low | Easy | Commercial |
| /general-dentistry/perio-protect | gum disease treatment southampton pa | low | Easy | Local |
| /patient-information/new-patients | dentist accepting new patients southampton | low | Easy | Local |
| /specials | dental membership plan southampton pa | low | Easy | Commercial |
| /about/dr-jeffrey-brenner | dr jeffrey brenner southampton | low | Easy | Branded |
| /about/dr-keyur-dudhat | dr keyur dudhat southampton | low | Easy | Branded |

### 13B. SEO — High-Volume "Near Me" Keywords (captured via GBP + service pages, NOT separate pages)

| Keyword | US Vol/mo | Cluster | Capture via |
| --- | --- | --- | --- |
| dentist near me | 673,000 | All | GBP + homepage |
| best dentist near me | 74,000 | All | GBP + reviews |
| family dentist near me | 40,500 | General | GBP + homepage |
| dental clinic near me | 40,500 | All | GBP categories |
| dental implants near me | 90,500 | Implants | /dental-implants + GBP |
| emergency dentist near me | 90,500 | Emergency | /emergency-dentistry + GBP |
| invisalign near me | 90,500 | Invisalign | /invisalign + GBP |
| cosmetic dentist near me | 40,500 | Cosmetic | /cosmetic-dentistry + GBP |
| teeth whitening near me | 49,500 | Whitening | /teeth-whitening + GBP |
| teeth cleaning near me | 49,500 | Cleaning | /general-dentistry + GBP |
| root canal near me | 40,500 | Endo | /root-canal + GBP |
| tooth extraction near me | 33,100 | Extraction | /tooth-extraction + GBP |
| dentures near me | 40,500 | Dentures | /dentures + GBP |
| veneers near me | 33,100 | Veneers | /porcelain-veneers + GBP |
| general dentistry near me | 4,400 | General | /general-dentistry + GBP |
| same day dentist near me | 1,600 | Emergency | /emergency-dentistry |
| same day emergency dentist near me | 480 | Emergency | /emergency-dentistry |
| clear aligners near me | 12,100 | Aligners | /invisalign + /clear-correct |
| general dentist near me | 9,900 | General | GBP + /general-dentistry |
| restorative dentistry near me | 2,400 | Restorative | /restorative-dentistry hub |

### 13C. Local SEO — City Targeting (Tier 1/2/3)

| City | Keyword | Vol | CPC | Tier | Page strategy |
| --- | --- | --- | --- | --- | --- |
| Southampton, PA | dentist southampton pa | 170 | $8.92 | 1 | Homepage primary (ranks #7 now) |
| Southampton (zip) | dentist 18966 | 40 | $6.21 | 1 | Homepage + footer + schema (trending up) |
| Warminster, PA | dentist warminster pa | 210 | $3.10 | 2 | /areas-we-serve/dentist-warminster-pa (highest vol) |
| Newtown, PA | dentist newtown pa | 210 | $2.65 | 2 | /areas-we-serve/dentist-newtown-pa (affluent) |
| Newtown, PA | dental implants newtown pa | 110 | $9.89 | 2 | High-value — mention on implants page + city page |
| Richboro, PA | dentist richboro pa | 170 | $3.43 | 2 | /areas-we-serve/dentist-richboro-pa |
| Huntingdon Valley | dentist huntingdon valley pa | 90 | $3.97 | 3 | /areas-we-serve/dentist-huntingdon-valley-pa |
| Feasterville, PA | dentist feasterville pa | 40 | $2.77 | 3 | /areas-we-serve/dentist-feasterville-pa |
| Newtown, PA | cosmetic dentist newtown pa | 40 | $0 | 2 | H2 on cosmetic page / city page |
| Holland, PA | dentist holland pa | 20 | $2.97 | 3 | /areas-we-serve/dentist-holland-pa (nearest) |
| Newtown | invisalign newtown pa | 30 | $0 | 2 | Mention on /invisalign |
| Churchville, PA | dentist churchville pa | 20 | $0 | 3 | Mention on Richboro page |

### 13D. AEO / AI Overview — Patient Questions (the FAQ + cost-content engine)

These drive the biggest measurable volume. Each becomes a 40–60 word answer block + FAQPage schema on the target page.

| Question | US Vol | Target page |
| --- | --- | --- |
| how much are dental implants | 49,500 | /dental-implants |
| what are dental implants | 40,500 | /dental-implants |
| how much does invisalign cost | 27,100 | /invisalign |
| invisalign cost | 74,000 | /invisalign |
| how much is invisalign | 40,500 | /invisalign |
| how much do dental implants cost | 9,900 | /dental-implants |
| invisalign vs braces | 18,100 | /invisalign |
| how does invisalign work | 8,100 | /invisalign |
| how long does invisalign take | 8,100 | /invisalign |
| how long do dental implants last | 3,600 | /dental-implants |
| do dental implants hurt | 2,900 | /dental-implants |
| does insurance cover invisalign | 4,400 | /invisalign |
| can invisalign fix overbite | 4,400 | /invisalign |
| does dental insurance cover implants | 3,600 | /insurance + /dental-implants |
| does invisalign hurt | 3,600 | /invisalign |
| tooth pain relief | 33,100 | /emergency-dentistry (first-aid block) |
| emergency tooth extraction | 5,400 | /emergency-dentistry |
| broken tooth repair | 4,400 | /emergency-dentistry |
| knocked out tooth | 320 | /emergency-dentistry (FAQ) |
| do emergency rooms have dentists | 260 | /emergency-dentistry (ER-vs-dentist FAQ) |
| how much does emergency dentist cost | 70 | /emergency-dentistry |
| teen invisalign | 880 | /invisalign |
| how to remove tartar without dentist | 6,600 | /blog (future) |
| how often should you go to the dentist | 1,900 | /general-dentistry |

### 13E. Google Ads — Campaign Keyword Themes (by phase)

Phase 1 — Brand Protection (exact match): brenner dental group, brenner dental, dr brenner dentist, dr jeffrey brenner, brenner dentist southampton, hampton family dental, hampton dental southampton pa

Phase 2 — High-Intent Services (phrase + exact):

- Emergency: emergency dentist near me, emergency dentist southampton, same day dentist near me

- Implants: dental implants near me, dental implants southampton pa, dental implants newtown pa, tooth implant southampton

- Invisalign: invisalign near me, invisalign southampton pa, invisalign cost

- Cosmetic: cosmetic dentist near me, teeth whitening near me, veneers near me

- Family/New patients: family dentist near me, dentist accepting new patients, best dentist near me

- General: root canal near me, tooth extraction near me, wisdom tooth removal

Phase 3 — Local Expansion: dentist richboro pa, dentist warminster pa, dentist newtown pa Phase 4 — Remarketing: site visitors + form abandoners + Performance Max (local)

### 13F. Google Ads — Negative Keywords (protect budget)

Career/education: jobs, job, career(s), hiring, salary, how to become, school, dental school, assistant, hygienist Cost-shoppers/wrong-fit: free, medicaid, medicare, charity, walmart, affordable (implants), aspen DIY/product: diy, at home, amazon, crest, whitening strips Geo (wrong area): philadelphia, new york, nyc, ny Brand confusion (critical for this project): hampton inn, hampton university, james hampton Research-only: images, pictures, wikipedia, definition, what is, meme, youtube, reddit Out-of-scope services: sedation, pediatric (practice doesn't offer), pet/vet/dog/cat

### 13G. GBP — Profile Keyword Setup (Google Business Profile)

- Name: Hampton Family Dental (no keyword stuffing)

- Primary category: Dentist

- Additional categories: Cosmetic Dentist, Dental Implants Periodontist, Emergency Dental Service, Orthodontist, Teeth Whitening Service, Dental Clinic (NOT Pediatric Dentist — excluded)

- Description (folds in brand bridge + towns + services): "Hampton Family Dental — formerly Brenner Dental Group — provides modern family, cosmetic, and emergency dentistry in Southampton, PA, serving Richboro, Warminster, Newtown, Holland, Feasterville, and Huntingdon Valley patients with implants, Invisalign, root canals, whitening, and same-day emergency care."

- Services to add (each ranks separately): General/Preventive/Family Dentistry, Dental Implants, Single Tooth Implant, All-on-4, Invisalign, Clear Aligners, Cosmetic Dentistry, Teeth Whitening, Porcelain Veneers, Smile Makeover, Root Canal, Tooth Extraction, Wisdom Tooth Removal, Dentures, Emergency Dentistry, Same-Day Emergency

- Service areas: Southampton, Holland, Richboro, Warminster, Newtown, Feasterville, Huntingdon Valley, Churchville, 18966

- Reviews: keep existing Brenner GBP (rename, don't recreate — saves reviews); request post-visit reviews; reply within 48h

### 13H. Brand & Bridge Keywords (transition, don't lose)

brenner dental group · brenner dental · dr brenner dentist · dr jeffrey brenner · brenner dentist southampton · brenner dental group southampton · hampton family dental · hampton family dental southampton pa · hampton dental southampton · dr keyur dudhat southampton → Capture via: brand-protection PPC + "formerly Brenner" on homepage/about/footer + 301 redirects from old brand URLs.

## 14. KEYWORD → PAGE QUICK INDEX (where each keyword "belongs")

- Homepage: dentist southampton pa, dentist 18966, family dentist near me, dentist near me, best dentist southampton

- Dental Implants: dental implants southampton pa, dental implants near me, dental implants newtown pa, full mouth implants, all-on-4, implant cost, how much are dental implants

- Emergency Dentistry: emergency dentist southampton pa, emergency dentist near me, tooth pain relief, broken tooth, knocked out tooth, same day dentist

- Invisalign: invisalign southampton pa, invisalign near me, invisalign cost, how much is invisalign, invisalign vs braces, teen invisalign, clear aligners

- Cosmetic hub: cosmetic dentist southampton pa, cosmetic dentistry near me, cosmetic dentist newtown pa

- General hub: general dentistry southampton pa, general dentist near me, teeth cleaning near me

- Restorative hub: restorative dentistry southampton pa, restorative dentistry near me

- Teeth Whitening: teeth whitening southampton pa, teeth whitening near me, professional whitening

- Dentures: dentures southampton pa, dentures near me, partial/full/implant dentures

- Crowns: dental crowns southampton pa, tooth crown, same day crown

- Fillings: dental fillings southampton pa, tooth colored fillings, cavity filling

- Root Canal: root canal southampton pa, root canal near me, painless root canal

- Extraction: tooth extraction southampton pa, wisdom tooth removal, emergency extraction

- Veneers: veneers southampton pa, porcelain veneers, veneers near me

- Clear Correct: clear aligners southampton pa, clearcorrect, invisible braces

- Perio Protect: gum disease treatment southampton pa, periodontal treatment, non surgical gum

- Specials: dental membership plan southampton pa, affordable dentist no insurance, dental savings plan

- City pages: dentist [richboro/warminster/newtown/holland/feasterville/huntingdon valley] pa

End of handoff. This document is now fully self-contained: narrative context (Sections 1–12) + complete keyword research (Sections 13–14). The Master Content Plan and Keyword Strategy workbooks remain the live working tools, but everything needed to brief, build, and continue is in this single scroll.